## Resource Work Analysis
Resource Workload Analysis Report
Generated by Gemini @ Today
Start Month | (All)
Due Month | (All)
Staus
| Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned | Assigned
Resources | Work Items | Estimate Hrs | Time Logged | Variance | Points | Avg. Points | Avg. Estimate | Avg. Logged | Avg. Variance
Anita Keller | 7 | 136 | 138.8 | -2.8 | 470 | 67.14 | 19.43 | 19.83 | -0.4
Anne Smith | 5 | 104 | 86.6 | 17.4 | 370 | 74 | 20.8 | 17.32 | 3.48
David Long | 5 | 44 | 46 | -2 | 120 | 24 | 8.8 | 9.2 | -0.4
Dele Sikuade | 2 | 12 | 24 | -12 | 30 | 15 | 6 | 12 | -6
Harvey Kandola | 4 | 40 | 31.4 | 8.6 | 120 | 30 | 10 | 7.85 | 2.15
Jane Montford | 10 | 116 | 120 | -4 | 350 | 35 | 11.6 | 12 | -0.4
Jim Bean | 9 | 192 | 197.6 | -5.6 | 680 | 75.56 | 21.33 | 21.96 | -0.63

## Data (hidden)
IssueKey | Project Name | ProjectCode | Title | Description | Reporter | Resources | Status | Priority | Severity | Resolution | Type | Revised | Created | Closed Date | Resolved Date | Due Date | Start Date | Percent Complete | Comments | Estimated Effort | Points | Component | FixedInVersion | AffectedVersionNumbers | Age | Repeated | Excess Time | Remaining Time | Time Logged | Votes | Visibility | Count() | Start Month | Due Month
[33 empty] | 01-00 | 01-00
Note on AH1: Calculated column NOT FROM Data

## Definitions (hidden)
Fields: | IssueKey | ProjectName | ProjectCode | Title | Description | Reporter | ResourceNames | Status | Priority | Severity | Resolution | Type | Revised | Created | ClosedDate | ResolvedDate | DueDate | StartDate | PercentComplete | Comments | EstimatedEffort | Points | ComponentNames | FixedInVersion | AffectedVersionNumbers | Age | Repeated | ExcessTime | RemainingTime | TimeLogged | Votes | Visibility | Count()
Url:
Date: | Today
Name: