## Project Work Estimates
Work Estimates Report
Generated by Gemini @ Today
| Start Month | (All)
| Due Month | (All)
|  |  | Work ITems | Time Logged | Estimated Effort | Avg. Logged | Avg. Estimate | Variance | Avg. Variance
| PROJA | Assigned | 8.469% | 348.4 | 352 | 13.4 | 13.54 | 3.6 | 0.14
|  | Closed | 6.515% | 291.4 | 276 | 14.57 | 13.8 | -15.4 | -0.77
|  | In Progress | 7.492% | 456.4 | 476 | 19.84 | 20.7 | 19.6 | 0.86
|  | In Test | 5.863% | 344.8 | 388 | 19.16 | 21.56 | 43.2 | 2.4
|  | Review | 8.469% | 406.4 | 420 | 15.63 | 16.15 | 13.6 | 0.52
|  | Unassigned | 5.212% | 356.8 | 200 | 22.3 | 12.5 | -156.8 | -9.8
| PROJA Total |  | 42.02% | 2204.2 | 2112 | 17.09 | 16.37 | -92.2 | -0.72
| PROJB | Assigned | 4.886% | 185.2 | 184 | 12.35 | 12.27 | -1.2 | -0.08
|  | Closed | 3.583% | 165 | 192 | 15 | 17.45 | 27 | 2.45
|  | In Progress | 3.583% | 97.6 | 116 | 8.87 | 10.55 | 18.4 | 1.68
|  | In Test | 4.235% | 243.2 | 212 | 18.71 | 16.31 | -31.2 | -2.4
|  | Review | 4.886% | 233.6 | 176 | 15.57 | 11.73 | -57.6 | -3.84
|  | Unassigned | 3.583% | 207.6 | 192 | 18.87 | 17.45 | -15.6 | -1.42
| PROJB Total |  | 24.76% | 1132.2 | 1072 | 14.9 | 14.11 | -60.2 | -0.79
| PROJC | Assigned | 5.863% | 331.2 | 304 | 18.4 | 16.89 | -27.2 | -1.51
|  | Closed | 4.235% | 270.4 | 232 | 20.8 | 17.85 | -38.4 | -2.95
|  | In Progress | 5.212% | 358.8 | 304 | 22.43 | 19 | -54.8 | -3.43
|  | In Test | 6.515% | 387.2 | 404 | 19.36 | 20.2 | 16.8 | 0.84
|  | Review | 5.863% | 217.4 | 268 | 12.08 | 14.89 | 50.6 | 2.81
|  | Unassigned | 5.537% | 177.6 | 188 | 10.45 | 11.06 | 10.4 | 0.61
| PROJC Total |  | 33.22% | 1742.6 | 1700 | 17.08 | 16.67 | -42.6 | -0.41
| Grand Total |  | 100% | 5079 | 4884 | 16.54 | 15.91 | -195 | -0.63
Data!R2:R1
Data!S2:S1
Note on XET41: R1 and R2 contain formulae that this sheet depends on

## Data (hidden)
IssueKey | Project Name | ProjectCode | Title | Description | Reporter | Test Run | Resources | Status | Priority | Severity | Resolution | Type | Revised | Created | Closed Date | Resolved Date | Due Date | Start Date | Percent Complete | Last Comment | Comments | Estimated Effort | Points | Component | FixedInVersion | AffectedVersionNumbers | Age | Repeated | Excess Time | Remaining Time | Time Logged | Votes | Visibility | Count() | Start Month | Due Month
[35 empty] | 01-00 | 01-00
Note on AJ1: Calculated column NOT FROM Data

## Definitions (hidden)
Fields: | IssueKey | ProjectName | ProjectCode | Title | Description | Reporter | Test Run | ResourceNames | Status | Priority | Severity | Resolution | Type | Revised | Created | ClosedDate | ResolvedDate | DueDate | StartDate | Percent Complete | Last Comment | Comments | EstimatedEffort | Points | Component | FixedInVersion | AffectedVersionNumbers | Age | Repeated | Excess Time | Remaining Time | Time Logged | Votes | Visibility | Count()
Url:
Date: | Today
Name: